## Project status
Component | Status | Notes
Authentication (sign in, sign up, password reset) | Real | Supabase Auth. Sign-up and sign-in confirmed working by the user.
Database schema with RLS | Real | Applied to Supabase project 'mailping'. Verified with rolled-back tests: mailbox limit, row isolation, blocked columns.
Server (server/) | Skeleton | Express with /health and /api/me. Not yet called from the frontend.
Mailboxes, Telegram, billing, settings, dashboard | Demo data | Screens work but show labelled demo data.
Gmail -> Telegram | PoC only | Verified only by the local proof of concept (poc/gmail-telegram).

## Next steps
# | Step | What it involves | Needs from you | Status
1 | Connect frontend to server and database | Preferences (user_preferences) read and saved in the real database through RLS; /api/me called with the user's token. | Confirm server/.env has SUPABASE_URL and SUPABASE_SECRET_KEY and 'npm run dev' in server/ listens on port 3001. Do not paste the key into chat. | Next
2 | Telegram | Connect by one-time link t.me/<bot>?start=<token>, status stored in the database, real test notification. Locally the server polls Telegram because there is no public webhook URL yet. | Telegram bot token in server/.env | Later
3 | Gmail OAuth on the server | Connect a mailbox, encrypt the refresh token, move polling from the PoC into a server background process, write to the notification log. | New OAuth client in Google Cloud | Later
4 | Stripe | Checkout, customer portal, webhooks. | Stripe account and keys | Later
5 | Google verification (restricted scope) | Start in parallel, because it takes the longest. | Decision to start | Later

## Open items
Item | Owner | Notes | Status
Run the Supabase security check | You | Dashboard > Advisors > Security. The advisors request was not approved earlier, so it has not been run. | Pending
Verify the password reset email flow | You | /reset-password has not been seen working yet. | Pending
Keep VITE_DEMO_MODE=true? | You | If true, unfinished screens keep labelled demo data while connected parts become real one by one. | Decision needed
Start step 1 (frontend to server and database) | Claude | Proposed as the next step, waiting for your go-ahead. | Pending